SMART PARKING PLATFORM

Semester Project Document

Software Requirements Specification and Project Management Plan

Prepared by $oftware ¢orp

Elisa Castillo

October 14, 2026

# Revision History

This table records every version of this document.

| Version | Date | Author | Summary of Changes |
| --- | --- | --- | --- |
| 0.1 | September 10, 2026 | Elisa Castillo | Initial draft. Worked on document structure, competitive analysis of existing parking platforms, the vision/scope section, and the fifteen use cases with a traceability table mapping each use case to the high level features. |
| 0.2 | September 17, 2026 | Elisa Castillo | Added Section 6 Project Schedule: work breakdown structure to level 3, estimation basis, project timeline with Gantt chart, milestone schedule, and key dependencies. Added the work breakdown numbering convention to Section 1.3. |
| 0.3 | September 24, 2026 | Elisa Castillo | Added Section 6.4 Product Backlog and Sprint Plan. Built the product backlog of 59 tasks across nine feature epics, derived from the use cases in Section 4.3 and the components in Section 6.1, and planned Sprint 1 around user authentication and live parking availability. Added the full backlog as Appendix A. |
| 0.4 | September 30, 2026 | Elisa Castillo | Added Section 8 Risk Management: the approach and rating scales, and a risk register of sixteen risks, four in each of the technical, schedule, financial, and people categories. Added Sections 9.2 and 9.3, the communication plan and the reporting method by audience. Added the risk numbering convention to Section 1.3. |
| 0.5 | October 7, 2026 | Elisa Castillo | Added Section 7 Budget, with 7.1 Resource and Cost Plan and 7.2 Budgeted Cashflow. Built a bottom up estimate priced from the twenty staff roles, and spread the total across four periods aligned to the schedule in Section 6.3. Added Sections 9.4 Roles and Resources and 9.5 RACI Matrix that assigns one accountable owner to each of the twenty five level 3 deliverables. |
| 0.6 | October 15, 2026 | Elisa Castillo | Expanded the use case catalog from 15 to 50 use cases in Section 4.3 and added the traceability table to the ten high level requirements. Restructured Section 6.3 into five two week sprints, added the milestone schedule, and added Section 6.5 Sprint Plan. Rebuilt the product backlog from 59 to 169 work items on 6.4 and Appendix A, each one assigned to a named team member. Added two roles and changed six in Section 9.4 and extended the RACI matrix on 9.5. |

# Table of Contents

Revision History	2

Table of Contents	4

1. Introduction	5

1.1 Purpose	5

1.2 Intended Audience	5

1.3 Document Conventions	5

2. Research and Competitive Analysis	6

2.1 Approach	6

2.2 SpotHero	6

2.3 ParkWhiz	6

2.4 ParkMobile	6

2.5 Summary Comparison	7

2.6 Opportunities for Differentiation	7

3. Vision and Scope	8

3.1 The Company	8

3.2 How the Project Was Acquired	8

3.3 Business Need	8

3.4 Scope	8

3.5 Out of Scope for Now	9

3.6 Project Constraints	9

4. Software Requirements Specification	9

4.1 Overall Description	9

4.2 Actors	10

4.3 Use Cases	10

4.4 Nonfunctional Requirements	14

4.5 External Interface Requirements	14

5. Stakeholder Analysis and Management	14

6. Project Schedule	15

6.1 Work Breakdown Structure	15

6.2 Estimation Basis	17

6.3 Project Timeline	18

6.4 Product Backlog	19

6.5 Sprint Plan and Sprint Backlogs	20

7. Budget	21

7.1 Resource and Cost Plan	21

7.2 Budgeted Cashflow	22

8. Risk Management	22

8.1 Approach and rating scales	23

8.2 Risk Register	23

9. Team Structure and Coordination	24

9.1 Delivery teams	24

9.2 Communication plan	25

9.3 Reporting method by audience	25

9.4 Roles and Resources	25

9.5 RACI Matrix	26

10. Appendices	26

Appendix A. Product Backlog	27

11. References	31

# 1. Introduction

## 1.1 Purpose

This document defines the vision, scope, requirements, and project management plan for the Smart Parking Platform, a system that helps drivers locate, reserve, and pay for parking spaces in parking garages in real time. It is a living document. New sections are added each week and existing sections are refined until the project is complete at the end of the semester.

## 1.2 Intended Audience

This document is written for the stakeholders of the project including drivers and vehicle owners, parking facility operators, city transportation departments, system administrators, finance and billing personnel, and the development teams at $oftware ¢orp. Business sections are written for a non technical audience and technical sections are written for the engineering and quality assurance teams.

## 1.3 Document Conventions

- Version numbers follow a simple decimal scheme. Draft versions begin at 0.1 and the final submitted version will be 1.0.

- High level features carry the prefix HLR, for example HLR-01.

- Use cases carry the prefix UC, for example UC-01.

- Tables and figures are numbered in sequence and carry a caption directly below them.

# 2. Research and Competitive Analysis

## 2.1 Approach

Before defining the scope of the Smart Parking Platform, $oftware ¢orp reviewed the parking applications that drivers already use today. Three products were selected because together they represent the main models in the market: a reservation marketplace for garages, a booking service built around guaranteed spaces, and a session based payment service for on street parking. Each product was reviewed for what it does well, where it falls short, and what that gap means for this project.

## 2.2 SpotHero

SpotHero is the best known parking reservation application in North America. A driver searches prices near a destination, pays ahead to hold a space, and then drives to the garage, lot or valet that was booked. The company advertises savings of up to fifty percent against the drive up rate, covers thousands of locations in cities including Houston, and integrates with Apple CarPlay so that a booking can be made without handling a phone. Business accounts keep work parking separate from personal parking and send receipts into expense systems.

Where it falls short: the spaces a driver sees are the ones an operator has listed for sale in advance, so the application reports sellable inventory rather than what is actually free inside the garage at that moment. Pricing moves with demand, and reviews of the parking applications describe rates rising sharply at busy times. The product is also built around the driver, and the tools offered to the operator who owns the garage are limited.

## 2.3 ParkWhiz

ParkWhiz follows a similar marketplace model with an emphasis on fast booking of guaranteed spaces, and it is frequently recommended alongside SpotHero for airport and event parking. Its strength is speed and certainty. A driver knows before leaving home that a specific space is held for them.

Where it falls short: it draws on much of the same aggregated inventory as its competitors, so coverage varies noticeably by city and by venue. Like SpotHero, it confirms that a reservation exists but does not tell a driver how full a garage is at this moment, and it offers little to the operator beyond a channel for selling unsold spaces.

## 2.4 ParkMobile

ParkMobile is the dominant application for on street and municipal parking. Drivers park, pay for a session from their phone, and extend that session remotely without returning to the meter. It is adopted widely by cities, which gives it very broad reach and strong name recognition among everyday commuters.

Where it falls short: it is designed around metered zones rather than garages, so garage reservation is not its core strength. Reviews of these applications describe notifications that arrive after a session has already expired and charges for sessions the driver believed had ended, which points to a reliability problem in the alerting and session tracking layer. Service fees added on top of the parking rate are a common source of complaints.

## 2.5 Summary Comparison

| Criteria | SpotHero | ParkWhiz | ParkMobile |
| --- | --- | --- | --- |
| Primary focus | Garage and lot reservations | Guaranteed prebooked spaces | On street and metered sessions |
| Advance reservation | Yes | Yes | Limited |
| Live garage occupancy | No, listed inventory only | No, listed inventory only | No |
| Navigation support | Yes, including CarPlay | Yes | Some |
| Operator tools | Limited | Limited | Limited |
| Common complaints | Surge pricing, billing errors | Uneven coverage by market | Late alerts, added fees |

## 2.6 Opportunities for Differentiation

- Accurate real time availability: rather than showing only the spaces an operator has listed for sale, the platform will report live occupancy from operator systems and sensor feeds, so a driver sees what is actually free right now.

- Clearer pricing: the platform will quote one total price before a driver confirms a reservation, with any fees itemized and no surprise increases at busy times.

- Reliable alerts: notifications for reservation confirmation, arrival, expiration, and payment will be tied directly to the reservation lifecycle so that a driver is warned before a session ends rather than after.

- Stronger tools for parking operators: the administrative dashboard, occupancy reporting, and analytics will be treated as a core product rather than an afterthought, giving operators the pricing and utilization insight the existing consumer apps do not provide.

# 3. Vision and Scope

## 3.1 The Company

$oftware ¢orp is a software development studio that designs, builds, and delivers complete platforms for clients in the transportation and mobility sector. The studio operates with unlimited theoretical resources and budget, which allows the project to be planned around the best solution rather than around cost. Work is delivered by six teams: mobile application, web application, backend and API, mapping and location services, payment integration, and quality assurance and testing.

## 3.2 How the Project Was Acquired

The Smart Parking Platform was commissioned by a regional parking operator that manages a portfolio of downtown and airport garages, working in partnership with a city transportation department. The operator had been losing revenue to unsold spaces while drivers circled the same blocks looking for parking, and the city was measuring the resulting congestion in its downtown corridors. Neither party could solve the problem with the tools available to them, since the existing consumer parking apps sell reservations but return little usable data to the facilities themselves.

The operator issued a request for proposal for a platform that would serve both audiences at once. $oftware ¢orp was selected because the proposal treated the operator dashboard and the driver application as equal halves of a single system rather than building a consumer app and adding reporting later. The engagement covers full delivery of the platform, from requirements gathering through testing and release.

## 3.3 Business Need

Drivers lose a significant amount of time searching for parking. The search creates congestion, wastes time that could be spent elsewhere, and adds cars to streets that are already crowded. Parking operators face the other half of the same problem, since they lack the tools to monitor how full their facilities are, to set prices against real demand, and to improve the use of the spaces they already have. A garage can sit half empty while drivers circle the block outside it, because neither side can see what the other is doing.

The Smart Parking Platform solves that problem from both directions. It shows drivers which spaces are available at that moment, lets them reserve and pay before they arrive, and guides them to the space itself. It gives operators a live view of occupancy, control over their pricing, and reports that show how their facilities are actually used.

## 3.4 Scope

The first version of the Smart Parking Platform lets drivers and parking operators create accounts, verify their identity, and sign in securely. Drivers see the spaces available at participating garages on an interactive map, select a date and time, reserve a space, and pay for it with the digital payment methods built into the platform. The platform keeps a record of every reservation, makes receipts available, and sends confirmations, arrival alerts, and reminders when a reservation is close to expiring.

Parking operators receive a dashboard that manages their facilities, updates availability, adjusts pricing, and reports on occupancy, utilization, demand patterns, and revenue. The platform also connects to external navigation services, so drivers receive directions to the garage they reserved.

## 3.5 Out of Scope for Now

- On street metered parking, parking zones, and municipal enforcement or citations.

- Electric vehicle charging reservation, metering, and billing.

- Valet services and attendant managed parking.

- Peer to peer sharing of private driveways and residential spaces.

- Manufacture of physical hardware such as occupancy sensors, cameras, and gate equipment. The platform integrates with this equipment but does not produce it.

- Monthly parking permits, corporate accounts, and subscription contracts.

- Autonomous vehicle self parking and automated valet features.

## 3.6 Project Constraints

- The development budget is theoretically unlimited, so scope is not constrained by cost.

- The timeline is fixed to the length of the semester and cannot be extended.

- The platform depends on third party services and APIs for mapping, navigation, and payment.

- The platform must comply with security and privacy requirements as well as applicable city ordinances and laws.

# 4. Software Requirements Specification

## 4.1 Overall Description

The Smart Parking Platform is a new system and does not replace an existing product at the operator or the city. It presents two faces on one shared backend. Drivers use a mobile and web application to find, reserve, and pay for a space, and parking operators use a dashboard to manage facilities, pricing, and reporting. Both faces read and write the same availability record, so a space sold to a driver leaves the operator view in the same moment.

Product perspective: A web and mobile platform on a shared backend, integrated with external mapping, navigation, and payment services and with the sensor and gate equipment already installed in participating garages.

Major functions: Account registration and secure sign in, parking search, live availability, reservation, digital payment, navigation to the garage, entry validation, reservation extension and cancellation, history and receipts, notifications, facility and pricing management, and occupancy and revenue analytics.

User classes: Drivers use the platform occasionally and receive no training, so the driver application has to work on the first attempt. Operators use it daily and need depth over simplicity. Finance and billing staff and system administrators use a narrow set of functions with elevated permissions.

Operating environment: iOS and Android for the driver application, current desktop and mobile browsers for the operator dashboard, and cloud hosted backend services.

Design constraints: Card data is held by the payment provider rather than by the platform. Location history is retained only for the period agreed with the city transportation department.

Assumptions and dependencies: Participating garages supply live occupancy data from their own equipment. Mapping, navigation, and payment are supplied by third parties under contract. Drivers carry a smartphone with location services enabled.

## 4.2 Actors

The platform has four primary actors, who sign in and act on the system, and three secondary actors, which are external systems that exchange data with it.

Primary actors

- Driver: Registers, searches for parking, reserves a space, pays, navigates to the garage, enters, extends or cancels, and retrieves receipts. The driver is the primary actor in thirty one of the fifty use cases.

- Parking Operator: Maintains facility details, availability, and pricing, and reads occupancy and revenue analytics from the dashboard.

- Finance and Billing Employee: Issues full or partial refunds for disputed charges and reconciles payouts to operators.

- System Administrator: Manages accounts, roles, and permissions, and monitors the health of the platform.

Secondary actors

- Payment Provider: Authorizes, captures, and refunds transactions, and holds card data on behalf of the platform.

- Mapping and Navigation Service: Supplies base maps, geocoding, and routing to the reserved garage.

- Garage Sensor and Gate System: Reports occupancy counts and entry and exit events, and validates a reservation at the gate.

Note: The city transportation department is a stakeholder rather than an actor. It receives aggregate reporting through the operator and does not sign in to the platform in the first version.

## 4.3 Use Cases

Each entry carries an identifier, the primary actor, the high level requirements it traces to, and the user story that states the goal and the benefit.

### 4.3.1 Accounts and Access

UC-01 Account Registration. Primary actor: Driver. Traces to HLR-01. Priority high. As a driver, I want to create and verify an account so that I can securely use the parking platform.

UC-02 Secure Sign In. Primary actor: Driver, Parking Operator. Traces to HLR-01. Priority high. As a driver or parking operator, I want to sign in securely so that I can access the features and information for my role.

UC-16 Profile and Vehicle Management. Primary actor: Driver. Traces to HLR-01, HLR-04. Priority high. As a driver, I want to manage my profile and my saved vehicles so that the correct plate is on the reservation that the gate reads.

UC-18 Single Sign On. Primary actor: Driver. Traces to HLR-01. Priority medium. As a driver, I want to sign in with an existing provider account so that I can start using the platform without creating another password.

UC-19 Account Deletion and Data Export. Primary actor: Driver. Traces to HLR-01. Priority high. As a driver, I want to delete my account and export my personal data so that I keep control of the information the platform holds about me.

### 4.3.2 Search and Availability

UC-03 Parking Search. Primary actor: Driver. Traces to HLR-03, HLR-10. Priority high. As a driver, I want to search for parking near a destination so that I can quickly find a convenient garage.

UC-04 Real Time Availability. Primary actor: Driver. Traces to HLR-02. Priority high. As a driver, I want to view current garage availability so that I can choose a location with open spaces.

UC-20 Saved and Favorite Garages. Primary actor: Driver. Traces to HLR-03. Priority low. As a driver, I want to save the garages I use often so that I can book a familiar location in a few taps.

UC-21 Filtered Search Results. Primary actor: Driver. Traces to HLR-03. Priority medium. As a driver, I want to filter search results by price, walking distance and amenities so that the list only shows garages that suit the trip I am making.

UC-22 Garage Detail View. Primary actor: Driver. Traces to HLR-03. Priority medium. As a driver, I want to see photos, clearance height, amenities and entrance details for a garage so that I know the space fits my vehicle before I pay.

UC-24 Waitlist for a Full Garage. Primary actor: Driver. Traces to HLR-02, HLR-09. Priority low. As a driver, I want to join a waitlist when a garage is full so that I am offered a space if one is released.

UC-25 Zone and Level Availability. Primary actor: Driver. Traces to HLR-02. Priority medium. As a driver, I want to see availability by level and zone inside a garage so that I drive straight to the part of the building that has space.

### 4.3.3 Reservation

UC-05 Parking Reservation. Primary actor: Driver. Traces to HLR-04. Priority high. As a driver, I want to reserve a parking space for a selected time so that a space is available when I arrive.

UC-09 Reservation Extension. Primary actor: Driver. Traces to HLR-04. Priority high. As a driver, I want to extend an active reservation so that I can remain parked longer without receiving an overstay charge.

UC-10 Reservation Cancellation. Primary actor: Driver. Traces to HLR-04, HLR-05. Priority high. As a driver, I want to cancel an upcoming reservation so that the space can be released and any eligible refund can be processed.

UC-11 Reservation History and Receipts. Primary actor: Driver. Traces to HLR-06. Priority medium. As a driver, I want to view my reservation history and retrieve receipts so that I can review and document my parking expenses.

UC-26 Future Reservation Scheduling. Primary actor: Driver. Traces to HLR-04. Priority high. As a driver, I want to book a space for a future date and time so that parking is secured for a trip I am planning.

UC-27 Reservation Modification. Primary actor: Driver. Traces to HLR-04. Priority medium. As a driver, I want to change the time or the vehicle on an upcoming reservation so that the booking matches my plans without cancelling and rebooking.

UC-29 Overstay Handling. Primary actor: Driver. Traces to HLR-04, HLR-05, HLR-09. Priority high. As a driver, I want to be warned before my reservation expires and charged a published overstay rate if I run late so that I am never surprised by the amount.

UC-30 No Show Release. Primary actor: Parking Operator. Traces to HLR-02, HLR-04. Priority medium. As a parking operator, I want an unclaimed reservation released after a grace period so that the space can be sold again instead of sitting empty.

### 4.3.4 Payments

UC-06 Digital Payment. Primary actor: Driver. Traces to HLR-05. Priority high. As a driver, I want to pay for a reservation digitally so that I can confirm my booking before arriving.

UC-15 Disputed Charge Refund. Primary actor: Finance and Billing Employee. Traces to HLR-05, HLR-06. Priority medium. As a finance and billing employee, I want to issue a full or partial refund for a disputed charge so that valid billing problems can be resolved and recorded.

UC-17 Saved Payment Methods. Primary actor: Driver. Traces to HLR-05. Priority high. As a driver, I want to save and remove payment methods so that I can check out without re entering card details every time.

UC-23 Total Price Quote. Primary actor: Driver. Traces to HLR-05. Priority high. As a driver, I want one total price with every fee itemized before I confirm so that the amount charged is the amount I agreed to.

UC-31 Promotion and Discount Codes. Primary actor: Driver. Traces to HLR-05. Priority low. As a driver, I want to apply a promotion code at checkout so that an advertised discount is reflected in the total I pay.

UC-32 Payment Retry and Alternate Method. Primary actor: Driver. Traces to HLR-05. Priority high. As a driver, I want to retry with another payment method when a charge is declined so that a failed card does not cost me the space I selected.

UC-33 Operator Payout Reconciliation. Primary actor: Finance and Billing Employee. Traces to HLR-05, HLR-08. Priority high. As a finance and billing employee, I want to reconcile platform revenue against operator payouts so that every garage is paid the correct amount on schedule.

UC-34 Account Credit. Primary actor: Finance and Billing Employee. Traces to HLR-05. Priority low. As a finance and billing employee, I want to issue account credit instead of a card refund so that goodwill cases are settled without a gateway transaction.

### 4.3.5 Mapping and Navigation

UC-07 Garage Navigation. Primary actor: Driver. Traces to HLR-10. Priority high. As a driver, I want directions to my reserved garage so that I can reach the correct entrance without unnecessary delays.

### 4.3.6 Sensor and Gate

UC-08 Entry Validation. Primary actor: Driver. Traces to HLR-04. Priority high. As a driver, I want my reservation validated at the garage entrance so that I can enter quickly and begin my parking session.

UC-28 Exit Validation and Session Close. Primary actor: Driver. Traces to HLR-04. Priority high. As a driver, I want the gate to recognize me on the way out and close my session so that the final charge is correct and the space is released.

### 4.3.7 Notifications

UC-12 Notification Preferences. Primary actor: Driver. Traces to HLR-09. Priority medium. As a driver, I want to configure notification preferences so that I receive useful confirmations, reminders, and expiration warnings through my preferred channel.

UC-35 Reservation Confirmation and Reminder. Primary actor: Driver. Traces to HLR-09. Priority high. As a driver, I want a confirmation when I book and a reminder before the reservation starts so that I do not forget a booking I already paid for.

UC-36 Expiration Warning with Extend Action. Primary actor: Driver. Traces to HLR-09, HLR-04. Priority high. As a driver, I want an expiration warning that lets me extend from the alert itself so that I can act before the session ends rather than after.

UC-37 Capacity Alerts for Operators. Primary actor: Parking Operator. Traces to HLR-09, HLR-02. Priority medium. As a parking operator, I want an alert when a facility is near capacity or full so that I can adjust pricing or open a reserved zone in time.

UC-38 Service Status and Incident Alerts. Primary actor: Driver, Parking Operator. Traces to HLR-09, HLR-10. Priority medium. As a driver or parking operator, I want to be told when a payment or mapping service is degraded so that I understand why part of the platform is not responding.

### 4.3.8 Operator Dashboard

UC-13 Facility and Pricing Management. Primary actor: Parking Operator. Traces to HLR-07. Priority high. As a parking operator, I want to manage facility details and pricing so that drivers receive accurate information and rates.

UC-39 Facility Profile and Hours. Primary actor: Parking Operator. Traces to HLR-07. Priority high. As a parking operator, I want to maintain facility profile details and operating hours so that drivers are never sent to a garage that is closed.

UC-40 Space, Zone and Accessibility Configuration. Primary actor: Parking Operator. Traces to HLR-07, HLR-02. Priority high. As a parking operator, I want to define spaces, zones and accessible spots so that availability and reservations reflect how the building is actually laid out.

UC-41 Manual Availability Override. Primary actor: Parking Operator. Traces to HLR-02, HLR-07. Priority high. As a parking operator, I want to override availability by hand so that a sensor failure does not oversell or undersell the garage.

UC-42 Operator Staff and Permissions. Primary actor: Parking Operator. Traces to HLR-07, HLR-01. Priority medium. As a parking operator, I want to create staff accounts with limited permissions so that attendants can look up reservations without reaching pricing or revenue.

UC-43 Desk Reservation Lookup. Primary actor: Parking Operator. Traces to HLR-07, HLR-04. Priority medium. As a garage attendant, I want to look up a reservation at the desk by plate or code so that a driver whose phone has failed can still be let in.

UC-44 Maintenance and Zone Closure. Primary actor: Parking Operator. Traces to HLR-07, HLR-02. Priority medium. As a parking operator, I want to close a zone for maintenance so that the platform stops selling spaces that are not usable.

### 4.3.9 Reporting and Analytics

UC-14 Occupancy and Revenue Analytics. Primary actor: Parking Operator. Traces to HLR-08. Priority high. As a parking operator, I want to view occupancy and revenue analytics so that I can improve facility utilization and pricing decisions.

UC-45 Report Export. Primary actor: Parking Operator. Traces to HLR-08. Priority medium. As a parking operator, I want to export occupancy and revenue reports so that I can take the figures into my own accounting and board reporting.

UC-46 Peak Demand Heat Map. Primary actor: Parking Operator. Traces to HLR-08. Priority medium. As a parking operator, I want a heat map of demand by day and hour so that I can set prices against the pattern rather than against a guess.

UC-47 Aggregate City Reporting. Primary actor: City Transportation Department. Traces to HLR-08. Priority medium. As a city transportation analyst, I want aggregate congestion and utilization figures with no personal data so that the city can measure the effect of the platform on downtown traffic.

UC-48 Scheduled Report Delivery. Primary actor: Parking Operator. Traces to HLR-08, HLR-09. Priority low. As a parking operator, I want reports delivered on a schedule so that the figures arrive without anyone remembering to pull them.

### 4.3.10 Platform Administration

UC-49 Platform Role Administration. Primary actor: System Administrator. Traces to HLR-01, HLR-07. Priority high. As a system administrator, I want to manage platform roles and permissions so that every account holds only the access its job requires.

UC-50 Platform Health Monitoring. Primary actor: System Administrator. Traces to HLR-10, HLR-09. Priority high. As a system administrator, I want to monitor platform health and the status of every external integration so that a failing provider is detected before drivers report it.

### 4.3.11 Traceability to the High Level Requirements

Every one of the ten high level requirements in the project brief is covered by at least two use cases. HLR-06 carries the fewest because reservation history and receipts are one screen and one service rather than a family of behaviors, and the refund path that also serves it is counted under HLR-05. HLR-04 carries the most because the reservation lifecycle is where the thirty five new use cases concentrated.

| Requirement | Description | Use cases | Traced use cases |
| --- | --- | --- | --- |
| HLR-01 | User registration and authentication | 7 | UC-01, UC-02, UC-16, UC-18, UC-19, UC-42, UC-49 |
| HLR-02 | Real time parking space availability | 8 | UC-04, UC-24, UC-25, UC-30, UC-37, UC-40, UC-41, UC-44 |
| HLR-03 | Interactive map displaying available parking locations | 4 | UC-03, UC-20, UC-21, UC-22 |
| HLR-04 | Parking reservation capability | 12 | UC-05, UC-08, UC-09, UC-10, UC-16, UC-26, UC-27, UC-28, UC-29, UC-30, UC-36, UC-43 |
| HLR-05 | Digital payment processing | 10 | UC-06, UC-10, UC-15, UC-17, UC-23, UC-29, UC-31, UC-32, UC-33, UC-34 |
| HLR-06 | Reservation history and receipts | 2 | UC-11, UC-15 |
| HLR-07 | Administrative dashboard for parking operators | 8 | UC-13, UC-39, UC-40, UC-41, UC-42, UC-43, UC-44, UC-49 |
| HLR-08 | Occupancy reporting and analytics | 6 | UC-14, UC-33, UC-45, UC-46, UC-47, UC-48 |
| HLR-09 | Notifications and alerts for users | 9 | UC-12, UC-24, UC-29, UC-35, UC-36, UC-37, UC-38, UC-48, UC-50 |
| HLR-10 | Integration with external mapping and navigation services | 4 | UC-03, UC-07, UC-38, UC-50 |

Table . Traceability from the ten high level requirements to the fifty use cases.

## 4.4 Nonfunctional Requirements

## 4.5 External Interface Requirements

# 5. Stakeholder Analysis and Management

This section identifies the parties affected by the Smart Parking Platform and sets out how each one is kept involved. Seven stakeholder groups are recorded. For each group the analysis names what the group needs from the platform, how much influence it holds over the decisions that shape it, the approach used to keep it engaged, and the channel and cadence through which it hears from the project, which ties back to the reporting method in Section 9.3.

| Stakeholder | Interest | Influence | Engagement | Channel and cadence |
| --- | --- | --- | --- | --- |
| Drivers and vehicle owners | True availability and price, and a space on arrival | Low each, high in aggregate | Usability testing in Sprints 2 and 4, acceptance testing in week 15 | In application notifications, every release |
| Parking facility operators | Selling unsold spaces, pricing to demand, live occupancy | High, signs off every milestone | Requirements workshop, sprint reviews, written phase sign off | Sprint review every two weeks, briefing monthly |
| City transportation departments | Less downtown circling, aggregate figures with no personal data | High on compliance | Requirements workshop, milestone reviews, aggregate reporting in UC-47 | Milestone review, weeks 4, 11, 13 and 15 |
| System administrators | Role and permission control, health of every integration | Medium, owns the console requirements | Role model review at design, acceptance of UC-49 and UC-50 | Backlog refinement before Sprint 5, weekly report |
| Finance and billing personnel | Refunds, chargebacks and payouts that reconcile | Medium, signs off payout reconciliation | Review of payment and refund flows, payout report in Sprint 4 | Weekly report, Sprint 3 and Sprint 4 reviews |
| Mobile application users | First attempt success on their own device | Low each, sets the quality bar | Device matrix testing, WCAG 2.2 AA pass in Sprint 5 | Pilot feedback from two garages, week 15 |
| Third party payment providers | Certified integration, card data off the platform | High on the schedule, certification gates release | Certification checklist in week 6, assessment booked for week 11 | Provider support channel, escalation per Section 9.2 |

Table . Stakeholder analysis and the engagement approach for each group.

Influence is read against the decisions this project makes rather than against the parking market. The operator, the city and the payment provider can stop a release, so each of the three is given a named point of contact and a fixed review. The driver groups cannot stop a release, but they decide whether the platform is used at all, so their engagement is built into testing.

# 6. Project Schedule

This section presents the work breakdown structure for the Smart Parking Platform and the schedule that is derived from it. The breakdown decomposes the platform into deliverables, the schedule places those deliverables into weeks, and the milestone table marks the points at which a group of deliverables is complete. The schedule covers fifteen working weeks. Week 1 begins Thursday August 27, 2026 and week 15 ends Wednesday December 9, 2026.

## 6.1 Work Breakdown Structure

1. Project Initiation and Planning

- 1.1 Requirements Elicitation

  - 1.1.1 Stakeholder Interviews

  - 1.1.2 Competitive Analysis

  - 1.1.3 Requirements Workshop with Operator and City

- 1.2 Vision and Scope Document

- 1.3 Software Requirements Specification

  - 1.3.1 Use Case Catalog

  - 1.3.2 Nonfunctional Requirements

- 1.4 Project Management Plan

  - 1.4.1 Work Breakdown Structure and Schedule

  - 1.4.2 Risk Register

  - 1.4.3 Communication Plan

- 1.5 Kickoff and Baseline Approval

2. System Design

- 2.1 Architecture Design

  - 2.1.1 Service and Interface Contract Design

  - 2.1.2 Database Schema Design

  - 2.1.3 Availability Data Model

- 2.2 Interface Design

  - 2.2.1 Driver Application Wireframes

  - 2.2.2 Operator Dashboard Wireframes

  - 2.2.3 Interactive Map Design

- 2.3 Security and Compliance Design

  - 2.3.1 Authentication and Authorization Model

  - 2.3.2 PCI DSS Scope Definition

  - 2.3.3 Data Retention Policy

3. Development

- 3.1 Backend and API Services

  - 3.1.1 Account and Authentication Service

  - 3.1.2 Availability Service

  - 3.1.3 Reservation Engine

  - 3.1.4 Notification Service

  - 3.1.5 Analytics and Reporting Service

- 3.2 Driver Application

  - 3.2.1 Registration and Sign In

  - 3.2.2 Parking Search and Interactive Map

  - 3.2.3 Reservation and Checkout

  - 3.2.4 Reservation History and Receipts

- 3.3 Operator Dashboard

  - 3.3.1 Facility and Pricing Management

  - 3.3.2 Live Occupancy View

  - 3.3.3 Occupancy and Revenue Reports

- 3.4 Mapping and Location Services

  - 3.4.1 Provider Abstraction Layer

  - 3.4.2 Geocoding and Garage Search

  - 3.4.3 Navigation Handoff

- 3.5 Payment Integration

  - 3.5.1 Hosted Payment Page and Tokenization

  - 3.5.2 Refund and Cancellation Handling

  - 3.5.3 Operator Payout Reconciliation

- 3.6 Sensor and Gate Integration

  - 3.6.1 Occupancy Feed Ingestion

  - 3.6.2 Entry Validation at the Gate

4. Testing

- 4.1 Unit Testing

- 4.2 Integration Testing

- 4.3 Load and Stress Testing

- 4.4 Security and Penetration Testing

- 4.5 User Acceptance Testing

5. Deployment

- 5.1 Environment Setup

- 5.2 Pilot Deployment to Two Garages

- 5.3 Production Release

6. Project Closure

- 6.1 Operator and Staff Training

- 6.2 Documentation Handover

- 6.3 Final Approval and Sign Off

## 6.2 Estimation Basis

Effort was estimated before the schedule was built. Each level 4 activity was sized in story points on the Fibonacci scale by the team that owns it, and those values were calibrated by analogy to earlier projects of comparable scope delivered by the studio. Story points measure complexity, risk, and effort rather than hours, so the conversion into calendar weeks was made afterward, once team assignments were known.

- Level 4 activities are the estimating unit. Level 5 tasks refine an activity and do not add to its total.

- Point values were calibrated by analogy to earlier studio projects of comparable scope.

- The development budget is theoretically unlimited, so staffing is not the constraint on the schedule. The fixed semester window is.

- Durations assume the six delivery teams work in parallel on their own branches, as described in Section 9.

- Estimates are revisited at every milestone, and any revision is recorded in the revision history at the front of this document.

## 6.3 Project Timeline

The schedule runs for fifteen working weeks and is grouped into four phases. The phases overlap only at their boundaries, so each one ends at a milestone that can be reviewed before the next begins.

| Phase | Weeks | Dates | Focus |
| --- | --- | --- | --- |
| Plan and requirements | W1 to W4 | Aug 27 to Sep 23 | Stakeholder elicitation, the fifty use case catalog, nonfunctional and interface requirements, risk and budget baseline, tooling and pipeline setup |
| Core build, Sprints 1 to 4 | W5 to W12 | Sep 24 to Nov 18 | Backend services, driver application, operator dashboard, mapping, payment and gate integration, delivered in four two week sprints |
| Hardening and system test, Sprint 5 | W13 to W14 | Nov 19 to Dec 2 | Administration and compliance work, accessibility and localization, end to end integration, load and stress testing, security and penetration testing |
| Acceptance and release | W15 | Dec 3 to Dec 9 | User acceptance testing, defect triage, pilot verification, production release, training and handover |

### 6.3.1 Milestone Schedule

Eight milestones replace the four phase gates used in version 0.5. Four of them sit at sprint reviews, which means the client sees working software at the gate rather than a status report about it.

| ID | Milestone | When | Completion criteria |
| --- | --- | --- | --- |
| M1 | Requirements baseline approved | Week 4, Sep 23 | SRS with 50 use cases, nonfunctional and interface requirements signed off by the operator and the city |
| M2 | Tooling and pipeline operational | Week 5, Sep 30 | Jira board, branching policy and the continuous integration pipeline running on every commit |
| M3 | Sprint 2 review, reservation hold demonstrated | Week 8, Oct 21 | A driver can search, select a garage and hold a space end to end |
| M4 | Sprint 3 review, paid reservation demonstrated | Week 10, Nov 4 | A driver can pay, navigate and enter through the gate |
| M5 | Feature complete | Week 12, Nov 18 | All High and Medium priority use cases are implemented and unit tested |
| M6 | PCI DSS assessment and penetration test cleared | Week 13, Nov 25 | External assessor evidence pack accepted |
| M7 | System test exit | Week 14, Dec 2 | Integration, load, security and accessibility testing complete, no open critical defects |
| M8 | Production release and handover | Week 15, Dec 9 | Pilot verified in two garages, production released, training and documentation handed over |

Table . Milestone schedule.

## 6.4 Product Backlog

The product backlog holds 169 work items, grouped into the six feature buckets the project has tracked since version 0.3. Login, UI, Backend and Reporting carry the delivery work. Testing holds the fifteen items that verify it. Then, project holds the fourteen governance, architecture and tooling items.

| Feature | Items | Story points | Minimum required | Status |
| --- | --- | --- | --- | --- |
| Login | 20 | 97 | 5 | Met |
| UI | 50 | 255 | 15 | Met |
| Backend | 49 | 318 | 15 | Met |
| Reporting | 21 | 94 | 10 | Met |
| Testing | 15 | 99 | New bucket in 0.6 | Met |
| Project | 14 | 70 | New bucket in 0.6 | Met |
| Total | 169 | 933 |  |  |

Table . Backlog item counts against the minimum set for each feature.

The Epic column is the grouping the work carries on the board, and it cuts across the feature buckets, because a bucket such as UI spans the driver application, the operator dashboard and the administration console, and fifty screens under one epic would make the board unreadable. Twelve epics are in use, nine of them already existed on the board from version 0.3 and kept their names, so the fifty nine items that were already there stayed under the epic they were already in. That is why a few items sit where the feature bucket alone would not predict: the manual occupancy override is under Parking Search and Map and the rate rules engine is under Payments and Receipts.

| Key | Epic | Stories | Points |
| --- | --- | --- | --- |
| EP-01 | User Authentication | 20 | 90 |
| EP-02 | Parking Search and Map | 17 | 94 |
| EP-03 | Reservations | 13 | 84 |
| EP-04 | Payments and Receipts | 18 | 104 |
| EP-05 | Navigation and Entry | 10 | 60 |
| EP-06 | Notifications | 7 | 36 |
| EP-07 | Facility and Pricing Management | 12 | 63 |
| EP-08 | Operator Occupancy Dashboard | 6 | 35 |
| EP-09 | Reporting and Analytics | 20 | 91 |
| EP-10 | Platform Administration | 10 | 57 |
| EP-11 | Quality and Release | 18 | 117 |
| EP-12 | Project Governance | 18 | 102 |
|  | Total | 169 | 933 |

Table 8. Jira epics and the work ranked under each.

## 6.5 Sprint Plan and Sprint Backlogs

### 6.5.1 Sprint 1 Backlog

### 6.5.2 Jira Project Management

The commitment column below is the backlog pulled into each sprint.

| Sprint | Weeks | Sprint goal | Items | Points | Capacity | Load |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | W1 to W6 | A driver can register, sign in, and see live garage availability on a map. | 26 | 145 | 240 | 60% |
| Sprint 2 | W7 to W8 | A driver can search, pick a garage and hold a reservation, and an operator can manage a facility. | 25 | 154 | 240 | 64% |
| Sprint 3 | W9 to W10 | A driver can pay for a reservation, navigate to the garage and enter through the gate. | 32 | 186 | 240 | 78% |
| Sprint 4 | W11 to W12 | The reservation lifecycle closes end to end and the operator and finance reporting is in place. | 38 | 198 | 240 | 82% |
| Sprint 5 | W13 to W14 | Administration, accessibility, localization and the full regression and acceptance cycle. | 42 | 217 | 240 | 90% |
| Release | W15 | Pilot verification, production release, training and handover. | 6 | 33 | 115 | 29% |

Table 9. Sprint plan with committed points against measured capacity.

The board is held in Jira, in a Space called Scrum Project Management. Work is grouped by epic, and a pull request that closes a work item carries the item key in its title so that the board moves when the code merges rather than when somebody remembers to drag a card.

# 7. Budget

This section presents the cost of building the Smart Parking Platform and the schedule on which that cost is spent. The resource plan prices the team, the cost plan adds everything the team consumes, and the cashflow distributes the total across the fifteen week schedule. The budget is not a constraint on this project, since Section 3.6 sets it as theoretically unlimited, so the figure here exists to tell the operator what the platform cost to build rather than to cap what gets built.

## 7.1 Resource and Cost Plan

The estimate is built from the bottom up. Every line carries its own quantity and unit cost and the lines are summed, so each number traces back to the work package or purchase that produced it. Labor is priced from the roles in Section 9.4. Overhead is applied at twenty five percent of labor, and a contingency reserve of fifteen percent is added last, set above the middle of the usual range because the platform depends on third party mapping, payment, and sensor services.

## 7.2 Budgeted Cashflow

The total is spread across four periods of roughly four weeks, aligned to the phases in Section 6.3, so each period can be read against the work it pays for. Labor follows the staffing ramp such as light while the team is still eliciting requirements, full through the build, and tapering across the release weeks. Non labor costs land in the period that triggers them, which is why the compliance assessment sits in period three. The cashflow total and the cost plan total agree, and the check at the foot of the table confirms it.

# 8. Risk Management

This section presents the risk management approach for the Smart Parking Platform and the register that is derived from it. The rating scales assign a probability and an impact to every risk, the matrix converts that pair into a single risk level, and the register records the response strategy, the owner, and the current status for each entry. Sixteen risks are recorded, four in each of the four categories the project tracks: technical, schedule, financial, and people. The register is baselined at the end of the plan and requirements phase in week 4 and is reviewed every two weeks, so probability and impact are rescored as the project moves through the phases in Section 6.3.

## 8.1 Approach and rating scales

Every risk is scored on two five point scales, one for the probability that it occurs and one for the impact if it does. The two scores meet in a five by five matrix that resolves them into a single level of low, medium, high, or extreme, so a rare risk with severe consequences and a frequent risk with minor ones do not end up at the same priority. Each risk is then given one of four responses: avoid, mitigate, transfer, or accept.

## 8.2 Risk Register

# 9. Team Structure and Coordination

The Smart Parking Platform is delivered by six teams working in parallel, so information has to move between them on a fixed rhythm rather than on demand. This section names those teams, sets the meeting cadence each one follows, and defines what every audience receives and through which method. Counting the six team leads and the project manager, the project carries twenty one channels at the coordination level, so cross team decisions are made at a single weekly sync and the detail inside each team stays inside its own standup.

## 9.1 Delivery teams

The platform is delivered by six teams, each one owning a part of the system end to end and led by the team lead named in Section 9.4. Nineteen of the twenty four people in the resource plan sit inside these teams. The remaining five, the project manager, the business analyst, the solution architect, the user experience designer and the security and compliance specialist, work across all six rather than inside one.

| Team | Scope | Lead | People | Deliverables |
| --- | --- | --- | --- | --- |
| Mobile Application | Driver application on iOS and Android, from registration to checkout, navigation handoff and notifications | Ana Beltran | 3 | 3.2 Driver Application |
| Web Application | Operator dashboard and administration console, live occupancy, pricing and reporting screens | Hana Sato | 3 | 3.3 Operator Dashboard |
| Backend and API | Shared services: accounts, availability, reservation engine, notifications, analytics, gate and sensor feed | Daniel Osei | 4 | 3.1 Backend services, 3.6 Gate integration |
| Mapping and Location Services | Provider abstraction, geocoding, garage search, navigation handoff | Kofi Mensah | 2 | 3.4 Mapping services |
| Payment Integration | Hosted payment page and tokenization, refunds, payout reconciliation, PCI DSS scope | Rafael Costa | 2 | 3.5 Payment Integration |
| Quality Assurance and Testing | Test strategy and exit criteria, automated regression, integration, load and security testing, pipeline and release | Maya Thompson | 5 | 4. Testing, 5. Deployment |

Table 10. The six delivery teams, their scope, and the deliverables each one owns.

## 9.2 Communication plan

## 9.3 Reporting method by audience

## 9.4 Roles and Resources

## 9.5 RACI Matrix

# 10. Appendices

The appendices hold the listings that the body of this document refers to but cannot display in place without breaking the argument it is making. Each appendix is a complete record rather than a summary, so a reader who questions a figure in Section 6 or Section 9 can trace it to the rows that produced it. Every appendix is referenced at least once from the section it supports, and nothing is filed here that the body does not reference.

## Appendix A. Product Backlog

Appendix A lists the 169 work items in the product backlog, in the order they carry on the board. The feature counts in Table 7, the epic grouping in Table 8, and the sprint commitments in Table 9 are all derived from this listing. The item identifier carries its feature bucket as a prefix, the owner is the team member named in Section 9.4, and the status is the position of the item on the board in week 8.

| ID | Task | Points | Sprint | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| Login-1 | Create login screen UI | 3 | Sprint 1 | Ana Beltran | Done |
| Login-2 | Create account registration screen UI | 3 | Sprint 1 | Tyler Brooks | Done |
| Login-3 | Implement email and password input validation | 2 | Sprint 1 | Tyler Brooks | Done |
| Login-4 | Add password encryption and secure storage | 5 | Sprint 1 | Sofia Moreno | Done |
| Login-5 | Integrate authentication API | 5 | Sprint 1 | Sofia Moreno | Done |
| Login-6 | Implement account verification by email or text code | 3 | Sprint 1 | Liam Walsh | Done |
| Login-7 | Implement forgot password reset flow | 3 | Sprint 1 | Liam Walsh | Done |
| Login-8 | Implement role based access for driver, operator, and finance | 5 | Sprint 2 | Daniel Osei | In Progress |
| Login-9 | Add multi factor authentication option | 5 | Sprint 2 | Nadia Farouk | To Do |
| Login-10 | Add session timeout and sign out | 3 | Sprint 2 | Liam Walsh | To Do |
| Login-11 | Implement single sign on with Google and Apple | 8 | Sprint 3 | Sofia Moreno | To Do |
| Login-12 | Build profile and vehicle management service | 5 | Sprint 2 | Liam Walsh | In Progress |
| Login-13 | Implement account deletion and personal data export | 8 | Sprint 5 | Sofia Moreno | To Do |
| Login-14 | Build saved and favorite garages service | 3 | Sprint 4 | Ravi Menon | To Do |
| Login-15 | Build operator staff account and permission service | 8 | Sprint 4 | Daniel Osei | To Do |
| Login-16 | Build platform role and permission administration service | 8 | Sprint 5 | Daniel Osei | To Do |
| Login-17 | Implement append only audit log for role, price and refund changes | 5 | Sprint 5 | Nadia Farouk | To Do |
| Login-18 | Add device trust and suspicious sign in detection | 5 | Sprint 5 | Nadia Farouk | To Do |
| Login-19 | Implement consent capture for location use and data retention | 5 | Sprint 3 | Nadia Farouk | To Do |
| Login-20 | Build account credit balance service | 5 | Sprint 5 | Ingrid Larsen | To Do |
| UI-1 | Create map screen UI with garage pins | 8 | Sprint 1 | Ana Beltran | Done |
| UI-2 | Add live availability overlay to map | 5 | Sprint 1 | Ana Beltran | Done |
| UI-3 | Create destination search and filter UI | 5 | Sprint 2 | Tyler Brooks | In Progress |
| UI-4 | Create garage detail screen UI | 5 | Sprint 2 | Tyler Brooks | To Do |
| UI-5 | Create booking flow screens UI | 8 | Sprint 2 | Ana Beltran | In Progress |
| UI-6 | Create active reservation screen with extend and cancel | 5 | Sprint 3 | Tyler Brooks | To Do |
| UI-7 | Create reservation confirmation screen with entry code | 3 | Sprint 2 | Tyler Brooks | To Do |
| UI-8 | Create checkout and wallet screen UI | 8 | Sprint 3 | Ana Beltran | To Do |
| UI-9 | Create reservation history and receipts screen UI | 5 | Sprint 3 | Priyanka Nair | To Do |
| UI-10 | Create refund screen UI for finance staff | 5 | Sprint 4 | Omar Haddad | To Do |
| UI-11 | Create navigation handoff from the app to the map provider | 5 | Sprint 3 | Ana Beltran | To Do |
| UI-12 | Create notification preferences screen UI | 3 | Sprint 3 | Priyanka Nair | To Do |
| UI-13 | Create pricing and rate editor UI | 5 | Sprint 3 | Hana Sato | To Do |
| UI-14 | Create facility management screens UI | 8 | Sprint 2 | Hana Sato | In Progress |
| UI-15 | Create reservation lookup screen UI for staff | 5 | Sprint 4 | Omar Haddad | To Do |
| UI-16 | Create space and zone configuration screen UI | 5 | Sprint 3 | Hana Sato | To Do |
| UI-17 | Create operator dashboard home UI | 8 | Sprint 2 | Hana Sato | In Progress |
| UI-18 | Create real time occupancy view by zone | 8 | Sprint 3 | Omar Haddad | To Do |
| UI-19 | Create profile and vehicle management screens | 5 | Sprint 2 | Tyler Brooks | In Progress |
| UI-20 | Create saved payment methods screen | 5 | Sprint 3 | Tyler Brooks | To Do |
| UI-21 | Create single sign on entry points on login and registration | 3 | Sprint 3 | Ana Beltran | To Do |
| UI-22 | Create account deletion and data export screen | 3 | Sprint 5 | Priyanka Nair | To Do |
| UI-23 | Create saved and favorite garages screen | 3 | Sprint 4 | Priyanka Nair | To Do |
| UI-24 | Create search filter panel for price, distance and amenities | 5 | Sprint 2 | Tyler Brooks | To Do |
| UI-25 | Add photo gallery, clearance and amenity detail to the garage screen | 3 | Sprint 3 | Priyanka Nair | To Do |
| UI-26 | Create price quote screen with itemized fee breakdown | 5 | Sprint 3 | Ana Beltran | To Do |
| UI-27 | Create waitlist join and status screen | 5 | Sprint 5 | Priyanka Nair | To Do |
| UI-28 | Create zone and level availability view for drivers | 5 | Sprint 4 | Ana Beltran | To Do |
| UI-29 | Create future reservation date and time picker | 5 | Sprint 3 | Tyler Brooks | To Do |
| UI-30 | Create reservation modification screen | 5 | Sprint 4 | Tyler Brooks | To Do |
| UI-31 | Create exit and session summary screen | 3 | Sprint 4 | Priyanka Nair | To Do |
| UI-32 | Create overstay warning and charge confirmation screen | 3 | Sprint 4 | Ana Beltran | To Do |
| UI-33 | Create promotion code entry in checkout | 3 | Sprint 5 | Tyler Brooks | To Do |
| UI-34 | Create payment retry and alternate method screen | 5 | Sprint 4 | Ana Beltran | To Do |
| UI-35 | Create account credit view for drivers | 3 | Sprint 5 | Priyanka Nair | To Do |
| UI-36 | Create in app notification center | 5 | Sprint 4 | Ana Beltran | To Do |
| UI-37 | Create extend from alert deep link flow | 5 | Sprint 4 | Tyler Brooks | To Do |
| UI-38 | Create facility profile and operating hours screens | 5 | Sprint 3 | Omar Haddad | To Do |
| UI-39 | Create accessible spot configuration screen | 5 | Sprint 4 | Omar Haddad | To Do |
| UI-40 | Create maintenance window and zone closure screen | 5 | Sprint 4 | Omar Haddad | To Do |
| UI-41 | Create operator staff and permission management screen | 5 | Sprint 4 | Hana Sato | To Do |
| UI-42 | Create payout and settlement screen for finance | 5 | Sprint 5 | Omar Haddad | To Do |
| UI-43 | Create platform administration console | 8 | Sprint 5 | Hana Sato | To Do |
| UI-44 | Create platform health and integration status screen | 5 | Sprint 5 | Hana Sato | To Do |
| UI-45 | Create aggregate city congestion report view | 5 | Sprint 5 | Omar Haddad | To Do |
| UI-46 | Create scheduled report configuration screen | 3 | Sprint 5 | Clara Vogel | To Do |
| UI-47 | Apply the WCAG 2.2 AA accessibility pass to the driver application | 8 | Sprint 5 | Noah Kim | To Do |
| UI-48 | Apply the WCAG 2.2 AA accessibility pass to the operator dashboard | 5 | Sprint 5 | Noah Kim | To Do |
| UI-49 | Build the English and Spanish language switch and locale formats | 5 | Sprint 5 | Priyanka Nair | To Do |
| UI-50 | Build the shared design system and component library | 8 | Sprint 1 | Noah Kim | Done |
| Backend-1 | Build occupancy feed ingestion from garage sensors | 13 | Sprint 1 | Daniel Osei | Done |
| Backend-2 | Implement live occupancy calculation per garage and zone | 8 | Sprint 1 | Daniel Osei | Done |
| Backend-3 | Create availability API for the applications | 5 | Sprint 1 | Sofia Moreno | Done |
| Backend-4 | Integrate geocoding and place search from the map provider | 5 | Sprint 2 | Lucia Ferrari | To Do |
| Backend-5 | Add operator manual occupancy override | 3 | Sprint 3 | Liam Walsh | To Do |
| Backend-6 | Build reservation state machine | 13 | Sprint 2 | Sofia Moreno | In Progress |
| Backend-7 | Implement hold, extend, and cancel logic | 8 | Sprint 2 | Sofia Moreno | In Progress |
| Backend-8 | Add double booking prevention with space level locking | 8 | Sprint 2 | Daniel Osei | To Do |
| Backend-9 | Integrate payment gateway in sandbox | 8 | Sprint 2 | Rafael Costa | In Progress |
| Backend-10 | Build rate rules engine for time based pricing | 8 | Sprint 3 | Ingrid Larsen | To Do |
| Backend-11 | Implement tokenized card capture | 8 | Sprint 3 | Rafael Costa | To Do |
| Backend-12 | Implement receipt generation and refund processing | 8 | Sprint 3 | Ingrid Larsen | To Do |
| Backend-13 | Create quote and total price API | 5 | Sprint 3 | Rafael Costa | To Do |
| Backend-14 | Implement geofencing and arrival detection | 5 | Sprint 4 | Kofi Mensah | To Do |
| Backend-15 | Build entry validation service for the gate | 8 | Sprint 3 | Daniel Osei | To Do |
| Backend-16 | Build routing and arrival estimate service | 5 | Sprint 3 | Lucia Ferrari | To Do |
| Backend-17 | Build push and email notification delivery service | 8 | Sprint 3 | Liam Walsh | To Do |
| Backend-18 | Add reservation reminder and expiration alerts | 5 | Sprint 4 | Liam Walsh | To Do |
| Backend-19 | Add full garage and near capacity alerts | 3 | Sprint 4 | Liam Walsh | To Do |
| Backend-20 | Build search filter and result ranking service | 5 | Sprint 2 | Lucia Ferrari | To Do |
| Backend-21 | Build garage detail, amenity and clearance service | 3 | Sprint 2 | Liam Walsh | To Do |
| Backend-22 | Build waitlist and space release service | 8 | Sprint 5 | Ravi Menon | To Do |
| Backend-23 | Extend the occupancy model to level and zone granularity | 8 | Sprint 3 | Kofi Mensah | To Do |
| Backend-24 | Build future reservation scheduling and capacity holds | 8 | Sprint 3 | Sofia Moreno | To Do |
| Backend-25 | Implement reservation modification rules and repricing | 5 | Sprint 4 | Ravi Menon | To Do |
| Backend-26 | Build exit validation and session close service | 8 | Sprint 4 | Ravi Menon | To Do |
| Backend-27 | Implement overstay detection and automatic charge | 8 | Sprint 4 | Rafael Costa | To Do |
| Backend-28 | Implement no show detection and automatic space release | 5 | Sprint 4 | Liam Walsh | To Do |
| Backend-29 | Build promotion and discount code engine | 5 | Sprint 5 | Ingrid Larsen | To Do |
| Backend-30 | Implement payment retry and alternate method handling | 5 | Sprint 4 | Ingrid Larsen | To Do |
| Backend-31 | Build operator payout and settlement reconciliation | 8 | Sprint 5 | Rafael Costa | To Do |
| Backend-32 | Build notification template store and channel routing | 5 | Sprint 3 | Liam Walsh | To Do |
| Backend-33 | Implement incident and service status broadcast | 5 | Sprint 5 | Jonas Weber | To Do |
| Backend-34 | Build facility profile and operating hours service | 5 | Sprint 2 | Liam Walsh | To Do |
| Backend-35 | Build space, zone and accessible spot configuration service | 5 | Sprint 3 | Ravi Menon | To Do |
| Backend-36 | Implement maintenance window and zone closure | 5 | Sprint 4 | Ravi Menon | To Do |
| Backend-37 | Build desk reservation lookup by plate or code | 5 | Sprint 4 | Ravi Menon | To Do |
| Backend-38 | Build platform health and integration status service | 5 | Sprint 5 | Jonas Weber | To Do |
| Backend-39 | Add geocoding cache and provider quota guard | 5 | Sprint 3 | Lucia Ferrari | To Do |
| Backend-40 | Build the mapping provider abstraction layer | 8 | Sprint 2 | Kofi Mensah | In Progress |
| Backend-41 | Implement accessible route and entrance selection | 5 | Sprint 4 | Lucia Ferrari | To Do |
| Backend-42 | Build license plate recognition handoff for entry and exit | 8 | Sprint 4 | Kofi Mensah | To Do |
| Backend-43 | Harden API rate limiting and abuse protection | 5 | Sprint 4 | Jonas Weber | To Do |
| Backend-44 | Implement data retention and purge jobs | 5 | Sprint 5 | Nadia Farouk | To Do |
| Backend-45 | Set up the continuous integration pipeline with build, test and static analysis | 8 | Sprint 1 | Jonas Weber | Done |
| Backend-46 | Set up the continuous delivery pipeline to staging and production with rollback | 8 | Sprint 2 | Jonas Weber | To Do |
| Backend-47 | Configure environments, secrets and infrastructure as code | 8 | Sprint 1 | Jonas Weber | Done |
| Backend-48 | Build the internal event stream for occupancy, reservation and payment events | 8 | Sprint 2 | Ravi Menon | To Do |
| Backend-49 | Implement database backup, restore and recovery rehearsal | 5 | Sprint 5 | Jonas Weber | To Do |
| Reporting-1 | Create occupancy report by day and hour | 5 | Sprint 4 | Clara Vogel | To Do |
| Reporting-2 | Create revenue report by facility | 5 | Sprint 4 | Clara Vogel | To Do |
| Reporting-3 | Create utilization and turnover metrics report | 5 | Sprint 4 | Clara Vogel | To Do |
| Reporting-4 | Add downloadable receipts for drivers | 3 | Sprint 3 | Liam Walsh | To Do |
| Reporting-5 | Create peak demand heat map view | 8 | Sprint 4 | Omar Haddad | To Do |
| Reporting-6 | Create pricing performance report | 5 | Sprint 5 | Clara Vogel | To Do |
| Reporting-7 | Create city transportation congestion summary report | 5 | Sprint 5 | Hana Sato | To Do |
| Reporting-8 | Create reservation and cancellation trend report | 5 | Sprint 4 | Clara Vogel | To Do |
| Reporting-9 | Create refund and dispute report for finance | 5 | Sprint 4 | Hana Sato | To Do |
| Reporting-10 | Implement scheduled report delivery by email | 5 | Sprint 5 | Liam Walsh | To Do |
| Reporting-11 | Create driver parking expense summary | 3 | Sprint 5 | Priyanka Nair | To Do |
| Reporting-12 | Add report export to CSV and PDF | 5 | Sprint 4 | Omar Haddad | To Do |
| Reporting-13 | Create zone and level occupancy report | 5 | Sprint 5 | Omar Haddad | To Do |
| Reporting-14 | Create waitlist conversion report | 3 | Sprint 5 | Clara Vogel | To Do |
| Reporting-15 | Create promotion performance report | 3 | Sprint 5 | Clara Vogel | To Do |
| Reporting-16 | Create overstay and no show report | 3 | Sprint 5 | Clara Vogel | To Do |
| Reporting-17 | Create accessible space utilization report | 3 | Sprint 5 | Hana Sato | To Do |
| Reporting-18 | Create payout and settlement report for finance | 5 | Sprint 5 | Hana Sato | To Do |
| Reporting-19 | Build the aggregate and anonymize layer for city reporting | 5 | Sprint 5 | Clara Vogel | To Do |
| Reporting-20 | Add role based data scoping to every report | 5 | Sprint 5 | Ravi Menon | To Do |
| Reporting-21 | Create platform health and uptime report | 3 | Sprint 5 | Jonas Weber | To Do |
| Testing-1 | Write the test plan with entry and exit criteria for each phase | 5 | Sprint 0 | Maya Thompson | Done |
| Testing-2 | Write acceptance criteria for the fifty use cases | 8 | Sprint 0 | Marco Delgado | Done |
| Testing-3 | Build the automated regression suite for registration and sign in | 5 | Sprint 2 | Chen Wei | In Progress |
| Testing-4 | Build the automated regression suite for reservation and payment | 8 | Sprint 3 | Chen Wei | To Do |
| Testing-5 | Build the automated regression suite for search and availability | 8 | Sprint 3 | Chen Wei | To Do |
| Testing-6 | Build the automated regression suite for the operator dashboard | 5 | Sprint 4 | Chen Wei | To Do |
| Testing-7 | Execute the cross device test matrix on the device farm | 8 | Sprint 4 | Diego Salinas | To Do |
| Testing-8 | Execute the integration test cycle across the six delivery teams | 8 | Sprint 5 | Diego Salinas | To Do |
| Testing-9 | Execute load and stress testing at three times measured peak | 8 | Sprint 5 | Chen Wei | To Do |
| Testing-10 | Execute the security and penetration test cycle | 8 | Sprint 5 | Nadia Farouk | To Do |
| Testing-11 | Execute accessibility conformance testing against WCAG 2.2 AA | 5 | Sprint 5 | Diego Salinas | To Do |
| Testing-12 | Run user acceptance testing with the operator and the city | 8 | Release | Maya Thompson | To Do |
| Testing-13 | Assemble and validate the PCI DSS evidence pack | 5 | Sprint 5 | Nadia Farouk | To Do |
| Testing-14 | Verify the pilot deployment in the two pilot garages | 5 | Release | Diego Salinas | To Do |
| Testing-15 | Run defect triage and the release readiness review | 5 | Release | Maya Thompson | To Do |
| Project-1 | Maintain the project document and the version history | 3 | Sprint 0 | Elena Ruiz | Done |
| Project-2 | Baseline the risk register and run the review every two weeks | 3 | Sprint 0 | Elena Ruiz | Done |
| Project-3 | Define the service and interface contracts between the six teams | 8 | Sprint 1 | Priya Raman | Done |
| Project-4 | Define the database schema and the availability data model | 8 | Sprint 1 | Priya Raman | Done |
| Project-5 | Define the authentication and authorization model | 5 | Sprint 1 | Priya Raman | Done |
| Project-6 | Define the PCI DSS scope boundary for the payment path | 5 | Sprint 1 | Nadia Farouk | Done |
| Project-7 | Run the requirements workshop with the operator and the city | 5 | Sprint 0 | Marco Delgado | Done |
| Project-8 | Maintain the use case catalog and the traceability matrix | 5 | Sprint 2 | Marco Delgado | To Do |
| Project-9 | Set up and administer the Jira project, boards, workflow and sprints | 5 | Sprint 0 | Mateo Rivas | Done |
| Project-10 | Define the branching model and the pull request review policy | 3 | Sprint 0 | Priya Raman | Done |
| Project-11 | Define the release checklist and the rollback procedure | 5 | Sprint 4 | Mateo Rivas | To Do |
| Project-12 | Produce the operator and staff training materials | 5 | Release | Elena Ruiz | To Do |
| Project-13 | Assemble the documentation handover package | 5 | Release | Elena Ruiz | To Do |
| Project-14 | Run the production release and the go live checklist | 5 | Release | Mateo Rivas | To Do |

Table A1. The complete product backlog, 169 work items carrying 933 story points.

# 11. References

https://spothero.com/

https://apps.apple.com/us/app/spothero-1-rated-parking-app/id499097243

https://winsparking.com/compare/parkwhiz

https://www.parkwhiz.com/how-it-works/

https://www.flashparking.com/demand-network/

https://parkmobile.io/parking/how-reservations-work

https://unstar.app/es-ES/blog/parkmobile-spothero-paybyphone-parkwhiz-passport-parking-apps-ranked-2026